## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://opensource-demo.orangehrmlive.com/index.php/pim/contactDetails/empNumber/7
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: OrangeHRM is the most popular open source human resource management (HRM) Web Based software application. Orange HRM, being browser based, require no clients to be installed. It has easy- to- use interface, is customizable to any length, and is affordable. The platform provides stability for performing rigorous Testing. In scope Functionality: Login with below credentials : 1. User should be able to Login to Orange HRM by entering valid credentials on Login Panel. User Name:Admin Password:Admin123 B. The PIM Module 1. The PIM Module should maintains all relevant employee related information, including different types of personal information, detailed qualifications, work experience, job related information etc. 2. The Admin should be able to Configure optional/custom fields, using Configuration Tab under PIM Module. 3. The Admin should be able to View all employee details 4. The Admin should be able to Add employee on the list. 5. The admin should be able to Generate employee report. 6. The ESS-Supervisor should be able to View his personal details as well as his/her subordinates. 7. The ESS-Employee can view his personal details under the ‘My Info’ Module. Out of Scope Functionality: Load Testing and Security Testing on Leave Management System. Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Stories
Issue Type | Summary
Login | As an already registered user,I should be able to login successfully and be able to explore and utilize the OrangeHRM services
Story 1 | As a registered user, I should be able to log in with either default credentials (Admin,admin123) or an already registered credentials for logging in successfully and be able to explore various services offered by OrangeHRM website.
Story 2 | As an unregistered user, I shouldn't be able to log into the website and explore various services offered by OrangeHRM website.
PIM Module | As an existing user, I should be able to explore and utilize various functionalities offered under the PIM section
Story 1 | AS an admin,I should be able to configure optional field
Story 2 | As a admin I should be able to configure fields.
Sub Task 1 | AS an admin,I should be able to configure optional field
Sub Task 2 | As a admin, I should be able to configure custom fields
Story 3 | AS an admin,I should be able to see all employee details so that all employee details are listed in tabular form
Story 4 | AS an admin,I should be able to add new employee
Story 5 | AS an admin,I should be able to generate employee report
Story 6 | AS an ESS-Supervisor,I want to see all subordinate employee details
Story 7 | AS a ESS-Employee,I want to see my personal details under 'My Info'
Story 8 | As a customer, I want to save a product in my wishlist so that I can view it again later

## Test Case Personal Details
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Results | Actual Result Iteration | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TS_TC_001 | View Employee Details | 1. URL "https://opensource-demo.orangehrmlive.com/" should be working 2. After loging into above url, dashboard should be displayed. | Verify viewing Employee Details | 1. Open URL "https://opensource-demo.orangehrmlive.com/" 2. Login as ESS employee 3. Click on 'My Info' |  | All the Personal Details should be displayed with required fields such as First Name, Middle Name, Last Name, Employee Id, Gender, Date Of Birth, Nationality, Marital Status. | For some employees, some of the field details are blank, all fields are not filled. | Fail

## Test Case Scenario
Test Cases For ESS Employee Personal Details
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TS_TC_001 | Dashboard page | 1. URL "https://opensource-demo.orangehrmlive.com/" should be working 2. User should login as an 'ESS Employee' | Verify Dashboard page | 1. Open url "https://opensource-demo.orangehrmlive.com/" 2. Enter credentials of ESS Employee and log in |  | After successfully logging in, user should be directed to dashboard page which should include navigation bar with fields as PIM,Leave, Time, My Info, Performance, Dashboard, Directory, Buzz. | After successfully logging in, user directed to dashboard page which include navigation bar with fields as PIM,Leave, Time, My Info, Performance, Dashboard, Directory, Buzz. | Pass
TS_TC_002 | My Info' tab | 1. URL "https://opensource-demo.orangehrmlive.com/" should be working 2. User should login as an 'ESS Employee' | Verify 'My Info' tab | 1. Open url "https://opensource-demo.orangehrmlive.com/" 2. Enter credentials of ESS Employee and log in 3. On navigation bar select 'My Info' tab |  | All the Personal Details should be displayed with required fields such as First Name, Middle Name, Last Name, Employee Id, Gender, Date Of Birth, Nationality, Marital Status. | All the Personal Details displayed with required fields such as First Name, Middle Name, Last Name, Employee Id, Gender, Date Of Birth, Nationality, Marital Status. | Pass
TS_TC_003 | Personal Details | 1. URL "https://opensource-demo.orangehrmlive.com/" should be working 2. User should login as an 'ESS Employee' | Verify viewing Personal Details | 1. Open url "https://opensource-demo.orangehrmlive.com/" 2. Enter credentials of ESS Employee and log in 3. On navigation bar select 'My Info' tab, in that select 'Personal Details'. |  | All ESS employees working under loged in supervisor will be displayed with fields as Name and Reporting Method. | All ESS employees working under loged in supervisor are displayed with fields as Name and Reporting Method. | Pass

## Test Scenario
Test Scenario for Sprint 1
Test Scenario ID | Requirement ID | Story Name | Test Scenario Description | Type of Testing | Possible No. of Test Case | Test case Details
TS_001 | OH_14 | Display ESS Employee Personal Details | View all the Personal Details of the ESS Employee | Funtional | 1 | Verify viewing employee details

## Defect Report
Defect Reporting For Sprint1
Defect Id. | Defect Summary | Module Name | Reported By | Date Found | Assigned To | Severity | Defect Priority | Status | Buildver | Reproduceable | Reprosteps | Expected | Actual
OH-34 | Some field details are blank by employee in My Info | My Info | jpreksha1510@gmail.com | 2020-12-22 | Shikha@gmail.com | Normal | low | To do | Sprint1 | Yes | 1. Go to URL "https://opensource-demo.orangehrmlive.com/" 2. Login as admin 3. On Navigation bar select 'My Info' | All the Personal Details should be displayed with required fields such as First Name, Middle Name, Last Name, Employee Id, Gender, Date Of Birth, Nationality, Marital Status. | For some employees, some of the field details are blank, all fields are not filled.

## Sheet1
Test Summary for Sprint1(27Nov - 2 Dec)
Sr No. | Activities | Count | Passed | Failed | Duplicates | Remarks
1 | Created Userstories | 1
2 | Created Testcases | 1
3 | Number of tests executed in Sprint1, iteration1 | 3 | 2 | 1
4 | Defects Reported | 1
5 | Number of sprints executed | 1
Any Challenges
Finding defect was time taking in My info tab as they have so many fields.

## Sprint 2
Automation Testing Case Study - 1
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
Url: http://demowebshop.tricentis.com
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Java Case study completion individually | 1. Case Study implementation code
| 2. Identify the Manual Test Cases that you want to automate. | 2. Test Cases: Positive & Negative
| 3. Plan the flow of application that you want to test using automation test scripts. | 3. Application Flows: Positive & Negative.
| 4. Create a Maven Project - Associate required libraries with the Maven Project | 4. Creation of project structure
5. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Parametrization Sample Data :
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Any Test Suite?
| 3. Implement parametrization using apache POI | 6. Test Runner class Parameters
| 4. Implement TestNG for generating reports and XML file for parallel execution of test suite | 7. Report File Names
5. Design the test runner class
Sprint Day 3 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements. | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 4 | 1. Generate Traceability Matrix based on Feature File User Stories, Test Scripts and Defects | 1. Traceability Matrix
| 2. Finally generate TestNG/XML Test report mentioning pass/fail status. | 2. Test Reports
| 3. Keep all code in Git repository | 3. Final execuatble code in Git
Sprint Day 5 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 6 | Sprint Evaluation